## Grant Transfer to UD
Award transfer in checklist
Transfer into UD | PI | DA | C&G | SRA | Sponsor
Non-sequential steps to transferring a sponsored project into UD:
Arrange initial meeting to identify the portfolio of award(s), coordinate checklist activities and path forward | X | X
Verify start date at UD (provide copy of signed offer letter to Research Office (RO) Contract & Grant Analyst (C&G)) | X | X
Provide award relinquishing statement from previous institution to RO C&G | X | X
Provide C&G with contact information of the Sponsored Programs Office at previous institution | X | X
Work with the Sponsored Programs Office at previous institution and the sponsor to coordinate activities for transfer | X | X | X
Process a proposal in PeopleSoft for the transfer application, inclusive of remaining cost share commitment (if applicable) and subaward documentation | X | X | X
Submit animal and/or human subject protocols to respective review boards | X
Submit transfer application to sponsor | * | * | X
Address follow-up questions from sponsor | * | * | X
Issue notice of award (NOA) to UD |  |  |  |  | X
Proceed with typical award setup process |  | X | X
* copied on communication