## Grant Transfer from UD
Award relinquishment/transfer out checklist
Transfer out of UD | PI | DA | C&G | SRA
Non-sequential steps to transferring a sponsored project out of UD:
Contact the Department Chair to notify them of your departure and discuss plans for sponsor project relinquishment or retention | X
Contact the Program Officer(s) to discuss plans for sponsored project relinquishment or retention | X
Communicate the plans for sponsored project relinquishment or retention to the assigned Department Administrator (DA) | X
Contact the assigned Contract & Grant Analyst (C&G) in the Research Office (RO) to notify them of sponsored project relinquishment or retention | * | X
Provide DA with the appropriate link to the Procedure for Sponsored Project (Award) Transfers | * |  | X
Review award notice(s) | X | X | X
Verify PI’s termination date at UD and start date at new institution |  | X | X
Complete the Sponsored Project Transfer Request for award(s) that will be relinquished (one per award) | X | X
Arrange meeting to coordinate checklist activities and path forward for each award | X | X | X
Review Sponsored Project Transfer Request(s) and secure RO approval |  |  | X
Discuss any technology developments with OEIP | X
Review equipment inventory for all equipment purchased on the award(s) | X | X
If permitted by the sponsor and approved by the Department Chair and Dean, work with the DA to initiate the Equipment Activity webform | X
Process Equipment Activity webform(s) for all equipment transferring to PI's new institution |  | X | X
Review personnel commitments, including researchers and graduate students, to determine if they will continue working on the award at UD. If so, a subaward agreement from the PI's new institution to UD will be needed. | X | X | *
Confirm any cost sharing commitments and determine what has been met and what will transfer to the PI's new institution | X | X | *
Contact the sponsor to discuss what is needed to complete the transfer, as applicable | * | * | X
Submit sponsor required transfer documents to your C&G for review | X | X
Contact the Sponsored Programs Office at the PI’s new institution to determine if they are willing to accept the award(s) (inclusive of all existing terms and commitments) and to coordinate the transfer | * | * | X
Request initiation of Automated Closeout Report (ACR) |  | X | *
Initiate ACR |  |  |  | X
Establish regular meetings with PI, DA and RO to discuss status of transfer(s), if needed |  | X | X
Review subaward(s) to determine if they have completed their scope of work. If not, notify new institution. | X
Contact the Sponsored Programs Office of subawardee(s) to notify them of the transfer and request closeout documentation per subaward terms (this could include final invoice, final technical report, final financial report, and/or closeout checklist) |  | X | *
Secure UD issued credit card from PI |  | X
Finalize all spending at UD | X | X
Complete ACR and submit to the Sponsored Research Accountant (SRA) |  | X
Review and process ACR |  |  |  | X
Finalize award balance to be transferred and submit required closeout documents to sponsor(s) | * | * | * | X
Ensure all sponsor required transfer documents are submitted | * | * | X
* copied on communication